## Sheet1
|  | 175 | 175 | 130 | 130 | 100
Task No | Task Description | PM | Architect | Backend Developer | Frontend Developer | Documenter | Total Hours | Technologies and Resources | Cost of Technology (per/month) | Number of required months | Total Cost
1 | Kickoff Meeting | [6 empty] | Linode Linux Webserver | 2060 | 2 | 4120
1.1 | Schedule Meeting | 1 |  |  |  |  | 1
1.2 | Publish Agenda | 1 | 1 |  |  |  | 2
1.3 | Attend Meeting | 3 | 3 | 3 |  | 3 | 12
1.4 | Publish meeting Minutes | 1 | 1 |  |  | 1 | 3
2 | Requirments Gathering | [5 empty] | 0
2.1 | Schedule Requirements Meetings | 2 | 2 |  |  | 2 | 6
2.2 | Prepare Questionnaire | 4 | 2 |  |  | 2 | 8
2.2.1 | Conduct Requirement interview (10, 2h eac) | 2 | 20 | 20 | 20 | 20 | 82
2.2.2 | Write Requirements Document | 2 | 20 | 8 | 8 | 40 | 78
3 | Design | [5 empty] | 0
3.1 | Design blueprint for development | 4 | 24 |  |  | 2 | 30
3.2 | Design blueprint for database structure | 4 | 8 |  |  | 2 | 14
3.3 | Design the Web UI | 1 | 8 | 8 | 8 | 2 | 27
3.4 | Specify other key component specifications | 2 | 8 |  |  | 8 | 18
3.5 | Design testing methods | 4 | 8 | 8 | 8 | 2 | 30
4 | Implementation | [5 empty] | 0
4.1 | Develop test scripts | 4 | 4 | 16 | 16 |  | 40
4.2 | Develop MySQL database | 4 | 8 | 32 | 32 |  | 76
4.2.1 | Test MySQL database | 1 | 1 | 2 | 2
4.2.2 | Documentation for MySQL database |  | 2 |  |  | 2
4.3 | Develop Javascript frontend | 4 | 4 |  | 20 |  | 28
4.3.1 | Test frontend | 1 | 1 |  | 2
4.3.2 | Documentation for frontend |  | 1 |  | 2 | 2
4.4 | Integration of frontend and backend | 4 | 4 | 16 | 16 |  | 40
4.4.1 | Test integrations | 4 | 4 | 4 | 4
4.5 | Develop installation scripts | 1 | 1 | 2 | 2
4.6 | Full product documentation | 1 | 2 |  |  | 8
5.1 | Live Deployment | 2 | 2 | 2 | 2 | 2
0
| Total hours | 57 | 139 | 121 | 142 | 98 | 557
|  | 9975 | 24325 | 15730 | 18460 | 9800 | 78290
| Total Cost | 82410
| Direct Expenses | 1000
| Contingency (10%) | 8241
91651